## Planilha1
Date | Activity_ID | Activity_name | Weight | Baseline | Progress | Planned_Value | Earned_Value | Actual_Cost | Cost_Variance | Schedule_Variance | Cost Performance_Index | Schedule_Performance_Index | Budget_at_Completion | Estimate_to_Complete | Estimative_at_Completion | Variation_at_Completion | To_Complete_Cost_Performance_Index | Planned_HH | Spend_HH | Planned_Hours | Spend_Hours
2021-01-15 | 1000 | Civil | 0.25 | 0.05 | 0.04 | 250 | 200 | 190 | 10 | -50000 | 1.05 | 0.8 | 5000000 | 5700000 | 5890000 | -890 | 998 | 250 | 200
2021-01-15 | 2000 | Mechanical | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2000000 | 2000000 | 2000000 | 0 | 1000
2021-01-15 | 3000 | Piping | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4000000 | 4000000 | 4000000 | 0 | 1000
2021-01-15 | 4000 | Electrical | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4000000 | 4000000 | 4000000 | 0 | 1000
2021-01-15 | 5000 | Instrumentation | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3000000 | 3000000 | 3000000 | 0 | 1000
2021-01-15 | 6000 | Commissioning | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2000000 | 2000000 | 2000000 | 0 | 1000
2021-01-15 | 10000 | Total | 1 | 0.01 | 0.01 | 250 | 200 | 190 | 10 | -50 | 1.05 | 0.8 | 20000000 | 20700000 | 20890000 | -890 | 999 | 250 | 200 | 250 | 200
2021-02-14 | 1000 | Civil | 0.25 | 0.15 | 0.1 | 750 | 500 | 700 | -200 | -250000 | 0.71 | 0.67 | 5000000 | 9450000 | 10150000 | -5150000 | 1047 | 750 | 500
2021-02-14 | 2000 | Mechanical | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2000000 |  | 0 | 2000000 | 1000
2021-02-14 | 3000 | Piping | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4000000 |  | 0 | 4000000 | 1000
2021-02-14 | 4000 | Electrical | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4000000 |  | 0 | 4000000 | 1000
2021-02-14 | 5000 | Instrumentation | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3000000 |  | 0 | 3000000 | 1000
2021-02-14 | 6000 | Commissioning | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2000000 |  | 0 | 2000000 | 1000
2021-02-14 | 10000 | Total | 1 | 0.04 | 0.03 | 750 | 500 | 700 | -200 | -250 | 0.71 | 0.67 | 20000000 | 9450000 | 10150000 | 9850000 | 1010 | 750 | 500 | 500 | 300
2021-03-16 | 1000 | Civil | 0.25 | 0.25 | 0.18 | 1250000 | 900 | 1000000 | -100 | -350000 | 0.9 | 0.72 | 5000000 | 6327160 | 7327160 | -2327160 | 1025 | 12500 | 10000 | 11750 | 9500
2021-03-16 | 2000 | Mechanical | 0.1 | 0.05 | 0.02 | 100 | 40 | 60 | -20 | -60000 | 0.67 | 0.4 | 2000000 | 7350000 | 7410000 | -5410000 | 1010 | 1 | 0.6 | 1 | 0.6
2021-03-16 | 3000 | Piping | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 0 | 0 | 0 | 0
2021-03-16 | 4000 | Electrical | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 0 | 0 | 0 | 0
2021-03-16 | 5000 | Instrumentation | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3000000 |  | 0 | 3000000 | 1000 | 0 | 0 | 0 | 0
2021-03-16 | 6000 | Commissioning | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 0 | 0 | 0 | 0
2021-03-16 | 10000 | Total | 1 | 0.07 | 0.05 | 1350000 | 940 | 1060000 | -120 | -410 | 0.89 | 0.7 | 20000000 | 13677160 | 14737160 | 5262840 | 1006 | 13500 | 10600 | 12750 | 10100
2021-04-15 | 1000 | Civil | 0.25 | 0.4 | 0.3 | 2000000 | 1500000 | 1800000 | -300 | -500000 | 0.83 | 0.75 | 5000000 | 5600000 | 7400000 | -2400000 | 1094 | 20000 | 18000 | 7500 | 8000
2021-04-15 | 2000 | Mechanical | 0.1 | 0.15 | 0.08 | 300 | 160 | 250 | -90 | -140000 | 0.64 | 0.53 | 2000000 | 5390625 | 5640625 | -3640625 | 1051 | 300 | 250 | 299 | 249.4
2021-04-15 | 3000 | Piping | 0.2 | 0.05 | 0.02 | 200 | 80 | 50 | 30 | -120000 | 1.6 | 0.4 | 4000000 | 6125000 | 6175000 | -2175000 | 992 | 200 | 500 | 200 | 500
2021-04-15 | 4000 | Electrical | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 0 | 0 | 0 | 0
2021-04-15 | 5000 | Instrumentation | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3000000 |  | 0 | 3000000 | 1000 | 0 | 0 | 0 | 0
2021-04-15 | 6000 | Commissioning | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 0 | 0 | 0 | 0
2021-04-15 | 10000 | Total | 1 | 0.13 | 0.09 | 2500000 | 1740000 | 2100000 | -360 | -760 | 0.83 | 0.7 | 20000000 | 17115625 | 19215625 | 784.375 | 1020 | 25000 | 21000 | 11500 | 10400
2021-05-15 | 1000 | Civil | 0.25 | 0.65 | 0.5 | 3250000 | 2500000 | 3400000 | -900 | -750000 | 0.74 | 0.77 | 5000000 | 4420000 | 7820000 | -2820000 | 1563 | 32500 | 34000 | 12500 | 16000
2021-05-15 | 2000 | Mechanical | 0.1 | 0.25 | 0.15 | 500 | 300 | 500 | -200 | -200000 | 0.6 | 0.6 | 2000000 | 4722222 | 5222222 | -3222222 | 1133 | 500 | 500 | 200 | 250
2021-05-15 | 3000 | Piping | 0.2 | 0.1 | 0.05 | 400 | 200 | 450 | -250 | -200000 | 0.44 | 0.5 | 4000000 | 17100000 | 17550000 | -13550000 | 1070 | 400 | 450 | 200 | -50
2021-05-15 | 4000 | Electrical | 0.2 | 0.05 | 0.05 | 200 | 200 | 150 | 50 | 0 | 1.33 | 1 | 4000000 | 2850000 | 3000000 | 1000000 | 987 | 200 | 150 | 200 | 150
2021-05-15 | 5000 | Instrumentation | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3000000 |  | 0 | 3000000 | 1000 | 0 | 0 | 0 | 0
2021-05-15 | 6000 | Commissioning | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 0 | 0 | 0 | 0
2021-05-15 | 10000 | Total | 1 | 0.22 | 0.15 | 4350000 | 3200000 | 4500000 | -1300000 | -1150000 | 0.71 | 0.74 | 20000000 | 29092222 | 33592222 | -13592222 | 1084 | 43500 | 45000 | 18500 | 24000
2021-06-14 | 1000 | Civil | 0.25 | 0.85 | 0.7 | 4250000 | 3500000 | 3500000 | 0 | -750000 | 1 | 0.82 | 5000000 | 1821429 | 5321429 | -321.429 | 1000 | 42500 | 35000 | 10000 | 1000
2021-06-14 | 2000 | Mechanical | 0.1 | 0.5 | 0.35 | 1000000 | 700 | 800 | -100 | -300000 | 0.88 | 0.7 | 2000000 | 2122449 | 2922449 | -922.449 | 1083 | 10000 | 800 | 9500 | 300
2021-06-14 | 3000 | Piping | 0.2 | 0.2 | 0.12 | 800 | 480 | 450 | 30 | -320000 | 1.07 | 0.6 | 4000000 | 5500000 | 5950000 | -1950000 | 992 | 800 | 450 | 400 | 0
2021-06-14 | 4000 | Electrical | 0.2 | 0.15 | 0.1 | 600 | 400 | 350 | 50 | -200000 | 1.14 | 0.67 | 4000000 | 4725000 | 5075000 | -1075000 | 986 | 600 | 350 | 400 | 200
2021-06-14 | 5000 | Instrumentation | 0.15 | 0.05 | 0 | 150 | 0 | 0 | 0 | -150000 |  | 0 | 3000000 |  | 0 | 3000000 | 1000 | 150 | 0 | 150 | 0
2021-06-14 | 6000 | Commissioning | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 0 | 0 | 0 | 0
2021-06-14 | 10000 | Total | 1 | 0.34 | 0.24 | 6800000 | 5080000 | 5100000 | -20 | -1720000 | 1 | 0.75 | 20000000 | 14168878 | 19268878 | 731.122 | 1001 | 68000 | 51000 | 24500 | 6000
2021-07-14 | 1000 | Civil | 0.25 | 0.95 | 0.8 | 4750000 | 4000000 | 3900000 | 100 | -750000 | 1.03 | 0.84 | 5000000 | 1157813 | 5057813 | -57.813 | 909 | 47500 | 39000 | 5000 | 4000
2021-07-14 | 2000 | Mechanical | 0.1 | 0.8 | 0.6 | 1600000 | 1200000 | 1000000 | 200 | -400000 | 1.2 | 0.75 | 2000000 | 888.889 | 1888889 | 111.111 | 800 | 16000 | 10000 | 6000 | 9200
2021-07-14 | 3000 | Piping | 0.2 | 0.3 | 0.25 | 1200000 | 1000000 | 1100000 | -100 | -200000 | 0.91 | 0.83 | 4000000 | 3960000 | 5060000 | -1060000 | 1034 | 12000 | 11000 | 11200 | 10550
2021-07-14 | 4000 | Electrical | 0.2 | 0.25 | 0.15 | 1000000 | 600 | 620 | -20 | -400000 | 0.97 | 0.6 | 4000000 | 5855556 | 6475556 | -2475556 | 1006 | 10000 | 620 | 9400 | 270
2021-07-14 | 5000 | Instrumentation | 0.15 | 0.15 | 0.07 | 450 | 210 | 200 | 10 | -240000 | 1.05 | 0.47 | 3000000 | 5693878 | 5893878 | -2893878 | 996 | 450 | 200 | 300 | 200
2021-07-14 | 6000 | Commissioning | 0.1 | 0.05 | 0.01 | 100 | 10 | 8 | 2 | -90000 | 1.25 | 0.1 | 2000000 | 15920000 | 15928000 | -13928000 | 999 | 100 | 100 | 100 | 100
2021-07-14 | 10000 | Total | 1 | 0.46 | 0.35 | 9100000 | 7020000 | 6828000 | 192 | -2080000 | 1.03 | 0.77 | 20000000 | 33476134 | 40304134 | -20304134 | 985 | 91000 | 68280 | 23000 | 17280
2021-08-13 | 1000 | Civil | 0.25 | 1 |  | 5000000 |  |  | 0 | -5000000 |  |  | 5000000 |  | 0 | 5000000 | 1000 | 50000 | 0 | 2500
2021-08-13 | 2000 | Mechanical | 0.1 | 0.9 |  | 1800000 |  |  | 0 | -1800000 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 18000 | 0 | 2000
2021-08-13 | 3000 | Piping | 0.2 | 0.5 |  | 2000000 |  |  | 0 | -2000000 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 20000 | 0 | 8000
2021-08-13 | 4000 | Electrical | 0.2 | 0.45 |  | 1800000 |  |  | 0 | -1800000 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 18000 | 0 | 8000
2021-08-13 | 5000 | Instrumentation | 0.15 | 0.25 |  | 750 |  |  | 0 | -750000 |  |  | 3000000 |  | 0 | 3000000 | 1000 | 750 | 0 | 300
2021-08-13 | 6000 | Commissioning | 0.1 | 0.1 |  | 200 |  |  | 0 | -200000 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 200 | 0 | 100
2021-08-13 | 10000 | Total | 1 | 0.58 |  | 11550000 |  |  | 0 | -11550000 |  |  | 20000000 |  | 0 | 20000000 | 1000 | 115500 | 0 | 24500
2021-09-12 | 1000 | Civil | 0.25 | 1 |  | 5000000 |  |  | 0 | -5000000 |  |  | 5000000 |  | 0 | 5000000 | 1000 | 50000 | 0 | 0
2021-09-12 | 2000 | Mechanical | 0.1 | 1 |  | 2000000 |  |  | 0 | -2000000 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 20000 | 0 | 2000
2021-09-12 | 3000 | Piping | 0.2 | 0.7 |  | 2800000 |  |  | 0 | -2800000 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 28000 | 0 | 8000
2021-09-12 | 4000 | Electrical | 0.2 | 0.6 |  | 2400000 |  |  | 0 | -2400000 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 24000 | 0 | 6000
2021-09-12 | 5000 | Instrumentation | 0.15 | 0.4 |  | 1200000 |  |  | 0 | -1200000 |  |  | 3000000 |  | 0 | 3000000 | 1000 | 12000 | 0 | 11250
2021-09-12 | 6000 | Commissioning | 0.1 | 0.25 |  | 500 |  |  | 0 | -500000 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 500 | 0 | 300
2021-09-12 | 10000 | Total | 1 | 0.7 |  | 13900000 |  |  | 0 | -13900000 |  |  | 20000000 |  | 0 | 20000000 | 1000 | 139000 | 0 | 23500
2021-10-12 | 1000 | Civil | 0.25 | 1 |  | 5000000 |  |  | 0 | -5000000 |  |  | 5000000 |  | 0 | 5000000 | 1000 | 50000 | 0 | 0
2021-10-12 | 2000 | Mechanical | 0.1 | 1 |  | 2000000 |  |  | 0 | -2000000 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 20000 | 0 | 0
2021-10-12 | 3000 | Piping | 0.2 | 0.8 |  | 3200000 |  |  | 0 | -3200000 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 32000 | 0 | 4000
2021-10-12 | 4000 | Electrical | 0.2 | 0.75 |  | 3000000 |  |  | 0 | -3000000 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 30000 | 0 | 6000
2021-10-12 | 5000 | Instrumentation | 0.15 | 0.6 |  | 1800000 |  |  | 0 | -1800000 |  |  | 3000000 |  | 0 | 3000000 | 1000 | 18000 | 0 | 6000
2021-10-12 | 6000 | Commissioning | 0.1 | 0.45 |  | 900 |  |  | 0 | -900000 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 900 | 0 | 400
2021-10-12 | 10000 | Total | 1 | 0.8 |  | 15900000 |  |  | 0 | -15900000 |  |  | 20000000 |  | 0 | 20000000 | 1000 | 159000 | 0 | 20000
2021-11-11 | 1000 | Civil | 0.25 | 1 |  | 5000000 |  |  | 0 | -5000000 |  |  | 5000000 |  | 0 | 5000000 | 1000 | 50000 | 0 | 0
2021-11-11 | 2000 | Mechanical | 0.1 | 1 |  | 2000000 |  |  | 0 | -2000000 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 20000 | 0 | 0
2021-11-11 | 3000 | Piping | 0.2 | 1 |  | 4000000 |  |  | 0 | -4000000 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 40000 | 0 | 8000
2021-11-11 | 4000 | Electrical | 0.2 | 0.9 |  | 3600000 |  |  | 0 | -3600000 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 36000 | 0 | 6000
2021-11-11 | 5000 | Instrumentation | 0.15 | 0.8 |  | 2400000 |  |  | 0 | -2400000 |  |  | 3000000 |  | 0 | 3000000 | 1000 | 24000 | 0 | 6000
2021-11-11 | 6000 | Commissioning | 0.1 | 0.7 |  | 1400000 |  |  | 0 | -1400000 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 14000 | 0 | 13100
2021-11-11 | 10000 | Total | 1 | 0.92 |  | 18400000 |  |  | 0 | -18400000 |  |  | 20000000 |  | 0 | 20000000 | 1000 | 184000 | 0 | 25000
2021-12-11 | 1000 | Civil | 0.25 | 1 |  | 5000000 |  |  | 0 | -5000000 |  |  | 5000000 |  | 0 | 5000000 | 1000 | 50000 | 0 | 0
2021-12-11 | 2000 | Mechanical | 0.1 | 1 |  | 2000000 |  |  | 0 | -2000000 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 20000 | 0 | 0
2021-12-11 | 3000 | Piping | 0.2 | 1 |  | 4000000 |  |  | 0 | -4000000 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 40000 | 0 | 0
2021-12-11 | 4000 | Electrical | 0.2 | 1 |  | 4000000 |  |  | 0 | -4000000 |  |  | 4000000 |  | 0 | 4000000 | 1000 | 40000 | 0 | 4000
2021-12-11 | 5000 | Instrumentation | 0.15 | 1 |  | 3000000 |  |  | 0 | -3000000 |  |  | 3000000 |  | 0 | 3000000 | 1000 | 30000 | 0 | 6000
2021-12-11 | 6000 | Commissioning | 0.1 | 1 |  | 2000000 |  |  | 0 | -2000000 |  |  | 2000000 |  | 0 | 2000000 | 1000 | 20000 | 0 | 6000
2021-12-11 | 10000 | Total | 1 | 1 |  | 20000000 |  |  | 0 | -20000000 |  |  | 20000000 |  | 0 | 20000000 | 1000 | 200000 | 0 | 16000
Formulas:
Date = +[Date, row above]